## v1
Somerville College Website Project Plan
| January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August
Week Beginning | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
Phase 1: Research & Site Architecture
Create project plan
Sign contract
Document current sitemap
Review current site content
Research Meetings
Put together full proposed sitemap
Client to review sitemap | [5 empty] | 12th
Client to feedback
Sign off on sitemap and overall site architecture
Phase 2: Design
Establish vision
Present vision | [7 empty] | 24th | 3rd | Governing body
Feedback on vision
Refine vision
Sign-off on vision
Design key page templates
Content requirements and brief drawn up
Review set of designs
Tweaks to designs
Sign-off on set of designs ready for build
Phase 3: Theme Development & Site Setup
Create HTML & CSS Page Templates
Setup and customise CMS
Phase 4: Content Management & Training
Collate content
Produce training vids teaching you how to use the CMS
Content loaded into site
Phase 5: Usability Testing & Tweaking
Round 1 feedback on site and CMS collated for desktop
Round 1 feedback addressed for desktop
Sign off on desktop site
Make website fully responsive
Round 2 feedback collated for mobile
Round 2 feedback addressed for mobile
Sign off on mobile site
Phase 6: Compatibility Testing & Launch
Test site on all browsers
Test on all devices
Go through pre-launch checklist
Somerville College security test TBC
Launch site
TWK
Somerville College
TWK and Somerville College
Key date for Sign Off
Dates to avoid
Half Term