Ratan Tata Building – Weekly look ahead

Site Manager:

25th May 2026

Site Enabling Works

|  |  | Involves |  |  |  |  |  |  |  |  |  | High | Medium | Low |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Heavy Plant & Equipment | Light Plant & Equipment | Noise | Emissions | Dust | Constant | Frequent | Occasional | One Oﬀ |  |  |  |
| Monday |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Bank Holiday |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No Works |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tuesday | Inspection of Archaeology |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Loading out to welfare (Wolfson) |  |  | X | X |  |  |  |  | X |  |  |  |  |
|  | Archaeology attendance |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gate hut |  |  | X | X |  |  |  |  | X |  |  |  |  |
| Wednesday | Removing Pavers |  |  | X | X |  |  |  | X |  |  |  |  |  |
|  | Grubbing up foundations |  | X | X | X | X |  |  |  | X |  |  |  |  |
|  | Loading out to welfare (Wolfson) |  |  | X | X |  |  |  |  | X |  |  |  |  |
|  | Archaeology attendance |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Open up brick arch / investigate |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gate hut |  |  | X | X |  |  |  |  | X |  |  |  |  |
| Thursday | Removing Pavers |  |  | X | X |  |  |  | X |  |  |  |  |  |
|  | Grubbing up foundations |  | X | X | X | X |  |  |  | X |  |  |  |  |
|  | Loading out to welfare (Wolfson) |  |  | X | X |  |  |  |  | X |  |  |  |  |
|  | Open up brick arch / investigate |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Archaeology attendance |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gate hut |  |  | X | X |  |  |  |  | X |  |  |  |  |
| Friday | Removing Pavers |  |  | X | X |  |  |  | X |  |  |  |  |  |
|  | Loading out to welfare (Wolfson) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Archaeology attendance |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Electrical installation cabins (Wolfson) |  |  | X | X |  |  |  |  | X |  |  |  |  |
|  | Gate hut |  |  | X | X |  |  |  |  | X |  |  |  |  |

Site Working Hours are from 08.00hrs to 17.00hrs - Monday to Friday

No Engines to Start on site before 08.00hrs

|  | Red noise levels likely to cause disturbance |
| --- | --- |
|  | Orange medium levels of noise, occasionally intrusive |
|  | Green noise levels unlikely to cause disturbance |